## Sheet1
ID | As a… | I want to be able to… | So that… | Priority | Sprint | Status
1 | User | view images from my phone | I don’t have to carry around photo albums with me if I want see the photos I have taken | 1 | 1 | To be started
2 | User | see the images sorted by date | I can find the photo I am looking for very easily | 2 | 2 | To be started
3 | User | zoom in or out of an image | I can magnify the small contents of an image | 2 | 2 | To be started
4 | User | see the properties of the image | I can see more information about an image | 3 | 3 | To be started
5 | User | crop an image | I can get rid of the unwanted part of an image | 3 | 3 | To be started
6 | User | rotate an image | I can fix the orientation of an image | 3 | 3 | To be started
7 | User | adjust the brightness of an image | I can fix overexposed or underexposed images | 3 | 4 | To be started
8 | User | adjust the contrast of an image | I can make fix highlights, shadows and textures of an image | 3 | 4 | To be started
9 | User | adjust the saturation of an image | I can make an image look dull or more vivid | 3 | 4 | To be started
10 | User | adjust the hue of an image | I can make colour corrections to an image | 3 | 4 | To be started